## Gap Analysis
Purpose and Objective: Document the existing state of the EForms team product backlog and scrum activities to improve the overall process and ensure smooth transition to the new Scrum Master
Current State | Gap | Recommendations
Product Backlog
The product backlog is maintain in a longstanding Azure DevOps project along with multiple others | No gap but any improvements must be made on an existing product backlog while making process improvements | The product backlog needs a complete refinement but there's no need to start fresh. Once it is completely refined and the team gets into a groove using it again, then slowly introduce other options and improvements to not interrupt any product progress.
Product Backlog Items and Bugs are both available on the backlog | N/A
PBIs and Bugs are added by manually by both the BAs and Devs | No gap with the creation but the team must ensure these are communicated and both PBIs and Bugs are kept up to date through refinement and as more details are uncovered
PBIs and Bugs appear to be automatically added to the next sprint | The product backlog is where work is prioritized, not an upcoming sprint board | Remove all items from the upcoming sprint. It looks like new PBIs are defaulting to the upcoming sprint when they are created so the team will just need to make sure they aren't assigned to it
PBIs and Bugs are properly linked to related work items | N/A
No PBI or Bug is owned by anyone on the team | Ideally the product owner should own everything as they split their time between stakeholders and the scrum team. | The BA team is working to split ownership amongst them. The scrum team probably knows who to work with at this point but it will help provide a reminder and visual if not. It will also help the BAs with any questions directed to them by stakeholders or leadership looking for status updates, progress, etc.
Items that are older than 2 years still remain active on the backlog | These are just clutter if they are no longer relevant | Do some sort of analysis, like: - Select a starting date and work backwards (e.g. anything older than 2020) - Check with the developers to see if the PBI/Bug is still relevant If they say yes: Acknowledge and let them know you’re confirming with the stakeholder (if there is one) Validate and confirm requirements with the stakeholder (if there is one) Prioritize on the product backlog It will likely be low priority but should still be given the same level of effort to prioritize as newer items If not: Ask the developers to provide a reason as to why it isn’t (e.g. no longer relevant, addressed in another PBI or bug fix, etc.) Validate with the stakeholder (if there is one) Add the reason to the PBI or Bug Change the state of the PBI or Bug to ‘Removed’ - Develop and follow a continuous cleanup cycle if needed Evaluate items that are not quite as old (anything from 2020-2021) Repeat every 6 sprints, 6 months, year, etc. for items that are X age
Ensure these are associated with a Feature so they are not lost
Incidents from ServiceNow are created as PBIs and could be either an update or enhancement or an actual bug | Incidents, by definition, would be bugs. The team has noted that incidents from ServiceNow could also be an entry put for other enhancements so this might be tricky to try and improve | Work with the team to understand this and develop a potential new process. There might be a tag or something else that could be used to help differentiate these.
Each PBI and Bug has a detailed title | N/A | N/A
Each PBI and Bug contains a detailed description and acceptance criteria
The team utilizes Smartsheet for requirements
The team actively adds notes to the discussion field
The team uses the state field, however they are going to re-evaluate to make sure they are using it effectively | The team is already working on defining these states, this is useful when refining the backlog and choosing what can be pulled into the sprint during sprint planning | The team is already working to define these but documenting them in a centralized location would be helpful for reference and any team turnover.
The product backlog prioritization isn't reviewed regularly and maintained through continual refinement | The team is going through refinement, but it appears to be just for new items. As a result, there are a lot of old and neglected items that might not be relevant and could be removed. | This is ultimately owned by the product owner, but this becomes a lot easier after the complete refinement. Ensure this is part of the normal day to day activities of the assigned BA.
The team is working on defining the priorities and a recommendation to help with PBIs or Bugs that are legal or compliance related, essentially a priority 1, the team might leverage Features
The team applies an effort by using planning poker | N/A | Define and document these in a centralized location
Effort for many PBIs and Bugs are missing | These are likely older PBIs and Bugs but any of these that will stay on the backlog need an effort | Catching up on these will be done through the complete refinement by the team but the product owner/BAs/scrum master need to ensure these are updated as part of day to day activities. This shouldn't be very high continuous effort.
The Value Area is always set to Business | No gap, however this could be an opportunity to track items differently
Most PBIs and Bugs have tasks associated but some are missing | Some might not need tasks, but anything where work will be needed should have tasks created and filled out appropriately/owned.
Not all tasks are owned by the development team
Tasks states are used and likely updated by moving the task through the sprint board lanes | N/A | Going forward, it would be beneficial to come up with a consistent plan of updated and/or moving tasks by the team. This will accurately update the burndown throughout the week.
The Remaining Work field is not consistently entered | This is required to accurately plan against capacity and track burndown. | All tasks need Remaining work so these need to be updated when new PBIs or Bugs with tasks are created and then become part of regularly product backlog refinement
Other fields such as hours worked, activity, blocked, and original estimate are not used | This is likely OK in the current state but there are opportunities to use these once the backlog is completely reviewed and refined | Once the team gets in a groove, look at ways to use these.
The team creates items for Dev Research, which are intended for researching future solutions | I'll work with the team understand these but there doesn't appear to be an outcome. If something would come out of this, like an improved process, potential update, etc., then that should be the PBI and Dev Research would be a task associated with the PBI | Evaluate this process. It might be too far down the road to do anything.
The team was not consistently using Features | Upon completing a PBI or Bug, the item wouldn't roll up or be associated with anything | Using Features will help group PBIs and Bugs together, both from the sprint backlog level and overall production backlog, which will help with reporting. Features can also have priorities.
When creating a PBI or Bug, link it to a feature right away
Review and update existing features then link any PBI and or Bug that is not yet linked, along with updating any existing link
Not all features are associated with an Epic | There are only 5 Epics but this could also help with grouping and organization | Ensure all updated features are associated to an epic but after PBIs and Bugs, then features, are all update first since this is lower priority
Current Spring Backlog
There is no clearly identified sprint goal | These would help the team get into the scrum mindset. An obvious goal and definition of done would be completing all tasks at the end of the sprint but there should be some output to prove the PBIs/Bugs are completed | Introduce both of these into sprint planning, starting with sprint 7. *Note* this was done for Sprint 7
There is no obvious 'Definition of Done'
Because PBIs and Bugs are unassigned, the corresponding sprint work item is not owned | This makes burndown measurements impossible during the sprint | This will become part of the regular process but is on the scrum master and PO/BAs to make sure these are updated through normal refinement so that needs to be understood
Because tasks are missing the remaining work value, the burndown cannot be calculated properly
Capacity was recently adjusted to account for sprint events and bugs | N/A | N/A
By just visuals, the sprint appears to have too many tasks and work items
The team moves tasks to completion once they complete the items
Scrum Event: Daily Scrum/Stand Up
The team has 8 meetings scheduled for 15 mins each during the sprint | N/A | The team is pretty efficient during these meetings so there isn't much to improve. By-the-book scrum says that the scrum master needs to make sure this meeting happens but they don't necessarily have to facilitate. There's nothing wrong with the facilitation but it's possible the team can follow an order or cadence each meeting without getting called on.
The team has been rotating facilitators because they are missing a scrum master
The team is effective at going through what you worked on, what your working on, and impediments
The team does screenshare during the stand up but don't seem like it is necessary |  | I'd challenge the visual of the sprint board, or at least of the first week of the sprint. The team should know what work is ahead coming off of the sprint planning session. It might be helpful during the second week of the sprint to see if any work can be reassigned or anything pulled forward.
The team has a '16 minute' for any items that need to be discussed in further detail
The team has self-resolved issues that could become impediments
Sprint 6 Observation: Brian Edwards was looking for more work | Not necessarily a gap and he deserves credit for speaking up and looking for more | Again this isn't a bad thing, Brian could've been super efficient this sprint, but it is worth investigating why and adjusting next sprint. He could've been under-planned.
Sprint 6 Observation: The QA team was very busy | This appeared to have an impact on what the dev team could do | Ask the team why QA was so busy and try to plan the upcoming sprint based on the feedback. See if there were outside non-sprint related factors.
Scrum Event: Sprint Planning
The team schedules one, 1.5 hour sprint planning | This is probably enough moving forward, Sprint 7 was a little unique because it was combining the Eforms and I-9 teams | Keep the meeting at 1.5 hours, that seems like a pretty safe time block and is already accounted for in the team's capacity
The team reviews the last sprint | Leave no task behind | It sounds like Brian will be reviewing these but any open tasks need to be either reassigned somewhere (likely the next sprint) or closed out.
Complete the PBIs when possible, but ensuring they are associated to a Feature.
New work is estimated | N/A | Continue to do these as they are needed for planning, the team is good at these discussions
The team created a sprint goal |  | Add a Defintion of Done to the sprint goal
PBIs and Bugs are assigned to sprints |  | Not much to improve upon and this will get easier once the merged team gets into a groove
PBIs and Bugs are prioritized in the spring backlog
The team picked PBIs to be demo'd in the sprint review | No real gap as there's not huge risk to demo, however if someone in the business is expecting a demo early in the sprint and it doesn’t happen it might raise some concerns | Continue to plan these in advance, I like this method. If for some reason something can't be demo'd then just take responsibility for it and improve for the next sprint.
The scrum master needed to create tasks for almost all PBIs | In this sprint planning case, it was pretty time consuming since many of the PBIs were repeated from past PBIs | I think this is possible but the BAs can create a generic PBI with the associate tasks and then copy it when there's a specific PBI needed. The team can assign a task owner and remaining hours in the upcoming planning session and/or add/remove tasks if needed
The team ran out of time assigning tasks |  | Not really a huge deal, the team has enough work to do and will continue the assignment process at the end of the stand ups which is a good solution
The Dev and QA teams volunteered to take on work and to be assigned tasks | N/A | This was good to see, ultimately the team decides what work is going to be done and who is going to do it. They simply just started taking on work on their own and didn’t need any pushing.
I-9 PBIs and Bugs were missing tasks and assignment details | A gap but understandable since the team just merged | The I-9 team added their PBIs and Bugs to the sprint backlog and should be able to improve upon them following the same steps the Eforms team is taking
It might be best for Amy to take a quick attempt at creating tasks, although she'd probably need to leverage Richard, Robert, and Igor
The I-9 product backlog should be cleaned up a bit, Amy mentioned this was in progress
Scrum Event: Backlog Refinement
The team schedules these sessions on a more ad-hoc basis but what seems to be consistent | No specific gap, the initial refinement did not last 1 hour. | 1 hour seems to be like enough time, so this is a 'if it isn't broke then don't fix it' scenario. Going through and refining the entire backlog should help keep this to an hour moving forward as well
The meeting is scheduled for 1 hour
The team invites the prod release team along with business users | I've never seen business users invited to this and will need to understand this more. There could be unnecessary influence on the team by including outside users; they don't own the product backlog. There was also one user that didn't talk at all, and not all items reviewed were applicable to all outside users, so it appeared to be a waste of their time. | Ultimately, when there is a product owner, they would be the voice of the business users. It might be hard to exclude these users but it might be time to start weening them off of this meeting. The prod release team might not be bad to keep involved, though.
New items are presented and the team votes on the effort | N/A | Since this time is already excluded from the team's capacity, using the full allotted time could be of benefit. This could involve reviewing older items or getting feedback on features, grouping items together, prioritization, etc. and trying to make incremental improvements to the backlog itself
Time permitting, existing items are reviewed
Sprint 6 observation: a few attendees did not contribute during the meeting | If attendees aren't making contributions, and this is the second time I've seen this, then they don't need to attend | If someone needs to be consulted on estimation then it would be more efficient to note it then follow up outside of the meeting
If it becomes routine where someone who is being consulted on estimation, then pull them back in, but understand that not everything discussed will pertain to them
Sprint 6 observation: the team does pretty well at working through estimations | N/A | In the case where there are multiple team members that are low or high with their estimates, ask a general question like 'what do the high estimators think?' as opposed to calling on them by name. This could allow them to vet out who shares there thoughts and might prevent some agreeing for the sake of agreement.
Scrum Event: Sprint Review
The sprint review is scheduled for 1 hour on the last day of the sprint | N/A | N/A
The review includes non-team members, e.g. stakeholders of the products
The team does demos, chosen during the refinement session by adding tasks and assigning them | Not really a gap, but the tasks should be moved to the In Progress column and given an estimate to stay consistent, maybe 0.25 hours | This is a good concept and I like that the team selected them the way they did this sprint
Following demos, the team 'walks the board', where they go item by item | I like this concept as well, but if you have tasks that are unassigned with no estimates then it might raise questions from the stakeholders | Do this same method next sprint but with owned PBIs and Bugs with each corresponding task having an owner and remaining work estimated while linked to the appropriate feature
The Walk the Board was done by a developer | This would ideally be a PO but in the interim should be a BA | Having a separation between developers/QA doing the demos and BAs doing the walk the board would demonstrate understanding of the scrum backlog in a visual way. The team has good chemistry within them, but here it could be demoed to stakeholders on the screen
The BA doing the walk the board could complete PBIs and Bugs while sharing their screen to give the team of sense of completeness and actually show the stakeholders that the items are completed
The walk the board was done in order of item on the sprint backlog | Also not necessarily a gap, but not each item is relevant to each stakeholder, so there's a chance someone has to wait to see their relevant items discussed | This would be difficult to account with because it generally makes sense to go in order, but if possible consider grouping related items with similar stakeholders together
The team was asked about an outcome of a PBI | This is something noted before, where if you create a PBI that doesn't have something defined as an outcome then someone might ask what was accomplished. The example is Dev Research…you're researching something for a reason, and that reason should be the PBI and dev research a task. | Hard to do, but try and ensure outcome based PBIs are created as much as possible. The Dev Research PBI is used across teams which complicates this.
A PBI was reviewed that took a developer and QA team member a day to work on | If this is the case, and it wasn't planned, this item would take away from planned work | Items can come in during a sprint but it would be beneficial to document and reference what other work was pushed as a result
A list of deployed or scheduled to be deployed items was displayed | Without a lack of 'Definition of Done', it is hard to see what could be considered done. Are items deployed during the sprint done? What about items where the work is completed but needs to be deployed in the coming days or weeks? | Define a definition of done and if something needs to be deployed then the board needs to account for it via a task if it isn't already
Scrum Event: Sprint Retro
The team holds a retro at the end of each sprint for 1 hour | N/A | The team should try and make actionable items. It's great collaboration but to make actual progress, there should be some action. An example is 'too many developer meetings', the action would be to 'reduce developer meetings during a sprint by ensuring the team is clear on requirements prior to the sprint starting'. This would be easy to measure because there should be less meetings scheduled by quantity.
The team tracks the conversation through Excel and by Start Doing, Stop Doing, and Keep Doing items

## Actions
Actions
3/9: Met with Jim, Elizabeth, Joe, an Brian to get overview of the team and backlog
3/14: Met with Elizabeth, Joe, and Brian to discuss backlog prioritization and restructure
3/21: Particpated in sprint planning, the team is assigning task owners and populating the Remaining Work and Orginal Estimate values in each which will accurately populate the burndown. For Prod Releases, the team decided to create a new PBI and separate tasks for the work done in the previous sprint. The PBI for the past sprint was linked to each corresponding task. The team will also close PBIs in the sprint review, so both ways will show the stakeholders progress was made